## Sheet1
ID | Date | User Story | State | Owner | Story Points | Comments
1 | 16-09-14 | Thinking of database design | cmt | Shilpa | 3
2 | 17-09-14 | Designing of tables | wip | Shilpa | 3
3 | 18-09-14 | Joining of tables with foreign | cmt | Shilpa | 2
keys
4 | 19-09-14 | Database diagrams | cmt | Shilpa | 2
5 | 22-09-14 | Architecture of web application and | wip | Ashutosh and Shilpa | 2
6 | 23-09-14 | Classes of tables are made in | cmt | shilpa | 2
the layer
7 | 24-09-14 | Designing of login page | wip | Ashutosh and Shilpa | 3 | Designing of logo is still left
8 | 25-09-14 | Design the logo and paste | cmt | Shilpa | 3 | Logo allignment is still left
change the color of buttons
9 | 26-09-14 | Study and done implementati- | cmt | Shilpa | 3 | Coding on the reset and login click is still left
|  | on of stored procedure and |  |  |  | will make a class in data acess layer and connect it with the web page
made a class in business layer
10 | 29-09-14 | Code for checking of correct | cmt | Shilpa | 3
user with correct password is
done through a database
11 | 30-09-14 | Designing of a master page | cmt | Shilpa | 2
with a bar and a footer
12 | 2014-10-01 | Designing of welcome page usi- | wip | Ashutosh and Shilpa | 3
ng a master page
13 | 2014-02-10 | Designing of a welcome page | cmt | Shilpa | 2
using a master page
14 | 2014-03-10 | Create a dropdown toggle on | cmt | Shilpa | 3
the navbar named Admin and
onclick of that admin dropdow
n owner page is opened
15 | 2014-06-10 | Create two buttons on the | cmt | Ashutosh and Shilpa | 3 | Modal is not working so proper designing of that age using tabs | is still left
ownerpage named property
and owner ,which will open
a popup when clicked
16 | 2014-07-10 | Binding of data in dropdown | wip | Ashutosh and Shilpa | 3
from database and all the data
is inserted in to the table in
database on savechanges click
17 | 2014-08-10 | Binding of data in dropdown | cmt | Ashutosh and Shilpa | 2
from database and all the data
is inserted in to the table in
|  | database on savechanges click | wip | Shilpa |  | Owner Details,form Location using tab,Grid showof Form Details
|  | and same will be done with |  |  |  | Register User,Login Ticket,Password encoding,busy symbol
owner click
18 | 2014-09-10 | Code for details of modified | cmt | Ashutosh and Shilpa |  | Same thing will be done for owner and will be saved in the Person table
by ,createdby,modified date,
created date for each entry
in the database Property table