## Sheet1
ID | Date | User Story | State | Owner | Story Points | Comments
1 | 16-09-14 | thinking of database design | cmt | Shilpa | 3
2 | 17-09-14 | designing of tables | wip | shilpa | 3
3 | 18-09-14 | joining of tables with foreign | cmt | shilpa | 2
keys
4 | 19-09-14 | database diagrams | cmt | shilpa | 2
5 | 22-09-14 | architecture of web application and | wip | ashutosh and shilpa | 2
6 | 23-09-14 | classes of tables are made in | cmt | shilpa | 2
the layer
7 | 24-09-14 | designing of login page | wip | Ashutosh and shilpa | 3 | designing of logo is still left
8 | 25-09-14 | design the logo and paste | cmt | shilpa | 3 | logo allignment is still left
change the color of buttons
9 | 26-09-14 | study and done implementati- | cmt | shilpa | 3 | coding on the reset and login click is still left
|  | on of stored procedure and |  |  |  | will make a class in data acess layer and connect it with the web page
made a class in business layer
10 | 29-09-14 | code for checking of correct | cmt | shilpa | 3
user with correct password is
done through a database
11 | 30-09-14 | designing of a master page | cmt | shilpa | 2
with a bar and a footer
12 | 2014-10-01 | designing of welcome page usi- | wip | ashutosh and shilpa | 3
ng a master page
13 | 2014-02-10 | designing of a welcome page | cmt | Shilpa | 2
using a master page
14 | 2014-03-10 | create a dropdown toggle on | cmt | Shilpa | 3
the navbar named Admin and
onclick of that admin dropdow
n owner page is opened
15 | 2014-06-10 | create two buttons on the | cmt | ashutosh and shilpa | 3 | modal is not working so proper designing of that age using tabs | is still left
ownerpage named property
and owner ,which will open
a popup when clicked
16 | 2014-07-10 | binding of data in dropdown | wip | ashutosh and shilpa | 3
from database and all the data
is inserted in to the table in
database on savechanges click
17 | 2014-08-10 | binding of data in dropdown | cmt | ashutosh and shilpa | 2
from database and all the data
is inserted in to the table in
database on savechanges click